## Slide 1: Learning Management System
Project of Team 12

## Slide 2: Charter
Official Project Name
  University LMS
Project Sponsor
  Ministry of High Education & Scientific Research

## Slide 3: Purpose
A multi-platform application and system that provides an easier way to manage and enhance the learning process specially in the collegial phase.

## Slide 4: Key Deliverables
For Students
  A website and a phone application where they can study, learn and be examined.
For Professors and TAs
  A dashboard which they put their materials and exams and get results that are enhanced by artificial intelligence to get better overview of the students’ progress
For University/College
  A general dashboard which it tracks students portfolios, profiles and grades.

## Slide 5: Project Resources
Initial Budget
  For servers components:
    2 Millions EGP
  Hired Developers
    Salary
Continuous Budget
  Maintenance Servers
    10 thousands EGP
  IT Managers
    Salary

## Slide 6: Assumptions
The application will be compatible with most popular phones versions and supports Android/IOS.

## Slide 7: High-Level Risks
Network failure of servers
Data Loss
Unwanted Access
  Modifying of grades
  Leaking of personal data

## Slide 8: Project Acceptance
Stability under heavy pressure
Interoperability and synchronization between other services.

## Slide 9: Exclusions
Any HR related dashboards for managing the workers and employees in the university.

## Slide 10: Work Breakdown Structure
  Starting
    Requirements
    Doing study about the project
    Plan the project
  Hardware and Software
    Operating System
    Testing Devices
  Coding
    Algorithm Design
    Coding the functions in all tasks
    Test Functions
    Interface the application
  Finishing
    Test the application
    Fixed Errors
    Finish the application
    Install the Application
    Training the administrators

## Slide 11: Responsibility Matrix

## Slide 12: Risks
Failure of the servers
  Solution: Keeping maintenance and emergency unit.
Unauthorized access
  Solution: Updating databases, increasing awareness about security.
Leaking of exams.
  Solution: optional use of AI to check others answers.

## Slide 13: Network
Activity | Description | Preceding Activity | Duration(Months)
A | Planning & Setting Environment | None | 3
B | Designing | A | 4
C | Implementation | A | 6
D | Testing | B & C | 3
E | Publishing Phase | D | 2
0 | A | 3
0 | Planning & Setting Environment | 
0 | 3 | 3
3 | B | 7
2 | Designing | 
5 | 4 | 9
3 | C | 9 | 
0 | Implementation |  | 
3 | 6 |  | 9
9 | D | 12 | 
0 | Testing |  | 
9 | 3 |  | 12
12 | E | 14 | 
0 | Publishing Phase |  | 
12 | 2 |  | 14

## Slide 14: Resources
ID | RES | DUR | ES | LF | SL | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
A | 2 | 3 | 0 | 5 | 2 | 2 | 2 | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  | 
B | 4 | 4 | 3 | 9 | 2 |  |  |  |  |  | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  | 
C | 2 | 6 | 3 | 9 | 0 |  |  |  |  |  | 1 | 1 | 1 | 1 |  |  |  |  |  |  |  | 
D | 3 | 3 | 9 | 12 | 0 |  |  |  |  |  |  |  |  |  | 3 | 3 | 3 |  |  |  |  | 
E | 2 | 2 | 12 | 14 | 0 |  |  |  |  |  |  |  |  |  |  |  |  | 2 | 2 |  |  | 
Total Resource Load |  |  |  |  |  | 2 | 2 | 2 | 2 | 2 | 4 | 4 | 4 | 4 | 3 | 3 | 3 | 2 | 2 |  |  | 
Resource Available |  |  |  |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4

## Slide 15: Budget Baseline
ID | Budget | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
A | 450 | 150 | 150 | 150 |  |  |  |  |  |  |  |  |  |  | 
B | 800 |  |  |  | 200 | 200 | 200 | 200 |  |  |  |  |  |  | 
C | 1300 |  |  |  | 250 | 250 | 250 | 150 | 100 | 300 |  |  |  |  | 
D | 1000 |  |  |  |  |  |  |  |  |  | 400 | 400 | 200 |  | 
E | 200 |  |  |  |  |  |  |  |  |  |  |  |  | 100 | 100
Total | 3750 | 150 | 150 | 150 | 450 | 450 | 450 | 350 | 100 | 300 | 400 | 400 | 200 | 100 | 100
Commutative |  | 150 | 300 | 450 | 900 | 1350 | 1800 | 2150 | 2250 | 2550 | 2950 | 3350 | 3550 | 3650 | 3750
ID |  |  |  |  |  | 
A | 150 | 150 | 100 |  |  | 
B | 200 | 200 | 200 | 200 |  | 
C | 250 | 250 | 250 | 150 | 100 | 300
D | 400 | 400 | 200 |  |  | 
E | 100 | 100 |  |  |  | 
Matrix of activity with cost
Chart: Cumulativa Baseline Budget (PV)
| Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14
Series 1 | 150 | 300 | 450 | 900 | 1350 | 1800 | 2150 | 2250 | 2550 | 2950 | 3350 | 3550 | 3650 | 3750 | 100

## Slide 16: Project Team
Zeyad Ahmed Ali
Zeyad Mohamed Hashem
Raed Reda Yaseen
Zeyad Walid El-Hosseiny
Zeyad Ali Mohamed
Romario Nageh
Zeyad Mohamed Hosny